VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

4.1 	Communications between the Contracting Authority and the Contractor shall be in writing in English and, in case of extremely urgency, can be anticipated via telephone call. The addresses designated by the Parties for that purpose are the following:

| Contracting Authority |  |
| --- | --- |
| Name | EUMM Georgia |
| Address | 49 Krtsanisi, Tbilisi 0114, Georgia |
| Contact person / Project Manager | …….. |
| Phone | ……… |
| E-mail | …….. |
| Contact person No. 1 (alternate) | …….. |
| Phone | ……… |
| E-mail | …….. |

| Contractor |  |
| --- | --- |
| Name |  |
| Contact person |  |
| Address |  |
| Phone |  |
| E-mail |  |

Article 5	Supervisor and Supervisor’s representative

The Contracting Authority’s Contract Manager as designated under Art. 4.1 shall directly act as the Supervisor of the works.

Article 7	Subcontracting

Sub-contracting is allowed up to 40% of the value of the Contract.

Article 9	Access to the site

For security-related reasons, the Contractor shall communicate 3 (three) working days in advance to the Contracting Authority/Project Manager the identity of the personnel that he intends to deploy on the site, so that any vetting process could be carried out time-wise.

Article 15	Performance guarantee

N/A

Article 16	Insurance

The Contractor shall establish a third party liability insurance covering damages to EUMM up to 10,000.00 euro per damage event or, pending/failing that, he shall be meant to have unconditionally  accepted to be self-insured without upper limit for damages to EUMM.

Article 17	Programme of implementation of tasks

17.1	The Contracting Authority will notify the contractor no later than 13 December 2014 about its final decision whether to implement or not the contract. Together with the notification and only in case the Contracting Authority decides to execute the contract, a Contract Commencement order will be issued establishing the starting date of the contract.

17.2	In case the Contracting Authority decides not to commence or implement the works both the Contracting Authority and the Contractor shall NOT be required to take any obligation under this contract. The contractor shall NOT be entitled to any compensation and shall NOT be allowed to any retribution.

17.3	The draft designs must be submitted to the Contracting Authority within 21 calendar days of Works Commencement order. The Contracting Authority shall, within 14 calendar days of receipt, notify the Contractor of its decision concerning the designs received giving reasons in case of amendments or rejection.

17.4	Cabling works shall commence in 5 working days upon the issuance of the Works Implementation Order by the Project Manager and counter signed by the contractor.

Article 20	Sufficiency of tender prices

The maximum overall price of the Contract and unit prices are fixed and not subject to revision.

Article 27	Demolished materials

Any demolished/removed materials, garbage or mess created (old plaster, paint buckets, cover materials, old carpet etc.) must be removed and disposed by the contractor upon finishing installations immediately.

Article 34	Period of implementation of tasks

34.1 	The maximum duration of the contract for elaboration of designs and implementation of works shall be 60 calendar days.

Article 36	Delays in the implementation of tasks

  - The rate of liquidated damages for delays in the completion of the Contract shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10% of the Contract price.

  - The rate of liquidated damages for delays in the completion of works set out in the relevant Commencement Order shall be 0.1% of the Commencement Order price for every day which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10% of the Commencement Order price.

Article 37    Amendments

Any amendment to this contract shall be implemented as laid down in Article 37 of the General Conditions.

Article 40	Origin and quality of works and materials

  - No restrictions whatsoever shall apply to the origins of the supplies and works.

  - The Contracting Authority reserves the right to demand, with reference to specific components and materials, the Contractor a preliminary technical assessment, prior to their incorporation in the works.

  - Applicable Georgian standard HSE (Hygiene, Safety and Environment) practices must be carried out throughout the project by the Contractor who will be responsible for the HSE on site, including “Tool Box” talks on safety, the issue of wearing and training of appropriate PPE (Personal Protection Equipment), and required safety practices. Hazardous materials have to be recorded and accounted for and kept in an appropriately safe environment. As with all HSE standards, records must be kept and available on site.

Article 41	Inspection and testing

The Contracting Authority reserves the right to inspect the site at any time to assess and test the state of art of the works with a view to give direction and guidance to fully meet the set technical specifications.

Article 44:	General principles for payments

44.1 	Payments shall be made in Euro (except if the contract is awarded to a local Contractor in which case any and all amounts payable shall be converted into Georgian Lari using the exchange rate applicable on the date of the transaction which is published on the InforEuro Webpage http://ec.europa.eu/budget/inforeuro/index.cfm?Language=en).

44.2	Payments shall be authorized and made by EUMM Finance Department to the bank account mentioned on the financial identification form completed by the Contractor against presentation of following documents:

a)	Original Invoice issued by the Contractor;

b)	Provisional Works Acceptance Certificate issued and signed by the Project Manager.

The Project Manager may at his own discretion issue Provisional Works Acceptance Certificate for the whole or any part of each Works Commencement Order fully respecting unit prices and measurement dimensions identified therein.

44.3	Due sums due shall be paid within 30 calendar days from the date on which an admissible payment request is registered by the EUMM Finance Department.

Article 46	Pre-financing

No pre-financing shall be granted to the Contractor for operations connected with the execution of the works.

Article 48	Price revision

The contract shall be at fixed unit prices which shall not be revised.

Article 49	Measurement

This is a unit-price contract.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notified by the Project Manager of the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.2	The duration of the defects liability period shall be 1 year after Provisional Works Acceptance Certificate is issued. The issuance of the partial Provisional Works Acceptance Certificates dates may be different depending on the date of completion of works for each stage.

Article 68	Dispute settlement

68.4

Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Brussels, Belgium.

* * *